## Slide 1: Ad Grants Online Marketing Challenge | Post-Campaign Report
7000 Languages
Neethu Narayanan | Ayyappa Reddy Satti | Jagruti Jangal Wagh | Srishti Kshirsagar Sopan | Anand Muraleedharan

## Slide 2: Executive Summary
1 | The campaign has run for last 5 weeks, and has received 30,665 impressions and 2347 clicks, with a budget of $7547.78.
2 | The overall CTR has been 7.66%, spanning between 4.91% - 10.66%.
3 | The major contributors were ‘females’ in the age-group of 18-24.
4 | With 66% overall impressions, 77% of the clicks were generated via Desktop alone.
5 | Interest on Wednesday has been comparatively higher; It has been the lowest in the weekends.

## Slide 3: Initial Campaign Structure
7000 Languages Brand - Week of March 11
Allocated Budget – $164/day
  Clicks – 379, Impressions – 5015
  Bidding Strategy – CPA
  CTR – 7.56%
  Language Specific Targetting
  Budget – $164/day
  Clicks – 54, Impressions – 506
  Bidding Strategy – Maximize Clicks
  CTR – 10.67%

## Slide 4: Week 1 - Campaign Overview
Campaigns | Daily Budget | Bidding Strategy | Clicks | Comments
7000 Languages Brand | $164 | Maximize Clicks | 365 | Changed bidding strategy
Language Specific Targeting | $32 | Maximize Clicks | 33 | Created new ad groups and added language specific ad copies
Driving Donations | $128 | Target CPA | 0 | Created new campaign with key words specific to language revival donations

## Slide 5: Week 1 - Achievements and Improvements
  Achievements:
  Successful utilization of the budget by proper reallocation and budgeting strategy
  Adding more relevant keywords improved the existing campaign – Language Specific Targeting
  Improvements and Goals:
  Change the bidding strategy to maximize the clicks
  Improve the ad-quality
  Target regions other than the USA and Canada

## Slide 6: Week 2 - Campaign Overview
Campaigns | Daily Budget | Bidding Strategy | Clicks | Comments
7000 Languages Brand | $144 | Target CPA | 328 | Looked at the average cost per click to come up with best bidding strategy
Language Specific Targeting | $32 | Maximize clicks | 40 | Worked on Ad-copy quality by adding language specific landing pages
Driving Donations | $64 | Target CPA | 0 | Experimented with various keywords and bidding strategies
7000 Languages Brand AU | $74 | Target CPA | 113 | Australia couldn’t be added to existing campaign due to vast geo-target

## Slide 7: Week 2 - Achievements and Improvements
  Achievements:
  Changing the bidding strategy from Maximize Clicks to CPA helped in increasing the number of clicks
  Demographic Experiment by creating a new campaign
  for Australia
  Number of clicks increased after implementing
  Structured Snippets in the ads
  Improvements:
  Improve the Driving Donations campaign
  Improve the ad-quality by using Dynamic Keyword Insertion

## Slide 8: Week 3 - Campaign Overview
Campaigns | Daily Budget | Bidding Strategy | Clicks | Comments
7000 Languages Brand | $124 | Target CPA | 283 | Addition of Structured Snippets, Device Bid Adjustment was added
Language Specific Targeting | $32 | Target CPA | 58 | Suggested for improvement of content on landing pages; Device Bid Adjustment was added
Driving Donations | $64 | Target Impression Share | 79 | Competitor Analysis, Dynamic Keyword Insertion since we had huge volume of keywords
7000 Languages Brand AU | $104 | Target CPA | 118 | Focused on Ad-quality improvement

## Slide 9: Week 3 - Achievements and Improvements
  Achievements:
  Number of impressions increased after changing the bidding strategy of Driving Donations from CPA to Target Impressions
  Number of impressions and clicks improved after we added new keywords by analyzing the competitor’s keywords
  Successfully implemented Dynamic Keyword Insertion
  Improvements:
  Reallocate budgets
  Improve Campaign Structure

## Slide 10: Week 4 - Campaign Overview
Campaigns | Daily Budget | Bidding Strategy | Clicks | Comments
7000 Languages Brand | $184 | Target CPA | 320 | Increased daily budget
Language Specific Targeting | $65 | Target CPA | 30 | Suggested for improvement of content on landing pages; Device Bid Adjustment was added
Driving Donations | $40 | Maximize clicks | 87 | Removed redundant and non-performing Keywords; Changed the bidding strategy
7000 Languages Brand AU | $32 | Target CPA | 76 | Compliance Issue with Location

## Slide 11: Week 4 - Achievements and Improvements
  Achievements:
  Effective utilization of the campaign budget
  Improved CTR in Drive Donations campaign
  Improved the overall structure of the campaigns by removing the redundant and non-performing keywords
  Improvements:
  Compliance issue with the 7000 Languages Brand AU campaign

## Slide 12: Week 5 - Campaign Overview
Campaigns | Daily Budget | Bidding Strategy | Clicks | Comments
7000 Languages Brand | $184 | Target CPA | 286 | Resolved issues with the AU Campaign; Added bid adjustments based on the 4 weeks campaign data
Language Specific Targeting | $65 | Target CPA | 26 | 
Driving Donations | $40 | Maximize clicks | 38 | 
7000 Languages Brand -2 | $32 | Target CPA | 69 | 

## Slide 13: Final Campaign Structure
7000 Languages Brand
Allocated Budget – $184/day
  Bidding Strategy – Target CPA
Driving donations campaign
Allocated Budget – $40/day
  Bidding Strategy – Maximize Clicks
7000 Languages Brand-2
Allocated Budget -$65
Bidding Strategy –Target CPA
  Language Specific Targetting
  Budget – $32/day
  Bidding Strategy – Target CPA

## Slide 14: 5 Weeks - Summary
CTR across different Campaigns By Device
Weekly Progress Clicks and Impressions
Weekly Budget utilization
Demographic division of clicks

## Slide 15: Core Performance Metrics
Proprietary + Confidential
Impressions
Clicks
Week-1
398
37
Conversions
Week-3
Week-4
538
513
40
49
7000
7051
Week-2
481
41
5978
4755

## Slide 16
Goals & Achievements
Ad-Grants Policy
Compliance
Attract
Traffic
Attract
Donors
1. Followed the Google Ads Policy Compliance Checklist
2. Scrutinized existing compliance issues
3. Resolved compliance issues
Improved overall ad impressions and clicks; meaningful reallocations across of budgets across campaigns
Successfully launched new campaign targeting donations which is now having around 1000 impressions weekly

## Slide 17: Marketing Goal Achievements and Social Impacts
7000 Languages is a non-profit that creates free language-learning software in partnership with Indigenous communities around the world so they can teach, learn, and revive their languages.
Created new campaigns and additional ad-groups in existing campaigns to promote language revival and learning
Ad-words campaign improved brand visibility and bridged the gap between language learners and the tools at their disposal
We strongly suggest to continue the campaign; Addition of conversion criteria by adding HTML tag to donation page should be done on priority.
Seasonal campaigns during Giving Tuesday, Year end and other special occasions would help in driving additional traffic.

## Slide 18: Recommended Next Steps
Source: Lorem ipsum dolor sit amet, consectetur adipiscing elit. Duis non erat sem
A
B
C
D
Further expand the footprint of the campaign across locations
A video on 7000 languages website; Addition of HTML tag on donations pages
Adjustment in 7000 languages brand awareness campaign should be made to change focus from impressions to conversions
Creation of seasonal campaigns

## Slide 19: Learning Component
Source: Lorem ipsum dolor sit amet, consectetur adipiscing elit. Duis non erat sem
Learning Objectives
Outcome
Group Dynamics
Client Dynamics
A great learning curve from setting up a campaign from scratch to shifting focus of existing campaigns to meet goals while being allied with compliance
Driving google ads campaign with objective of meeting business goals
Supported us through out the campaign by giving us freedom to make important decisions on campaign and helping us understand NGO mission
Following servant leadership and management by objective principles, we were able to build trust quickly and were able to drive innovative solutions faster

## Slide 20: Client’s Feedback